## Slide 1: NPOMF Project
Sharing Project Lessons

## Slide 2: Project purpose and objectives
Outcome
Improve the quality of life of Ngati Porou and vulnerable families living within the NI East Coast district.
NI East Coast a top priority areas for children at risk
TRONPnui work with 4000 individuals and/or whānau within the district and we need to understand what is and isn’t working through a repeatable evidence base
Outputs
A NPOMF to understand if investments and actions are improving the quality of life for vulnerable families
Access, test and overlay Government’s big data with Whanau Oranga programme data to understand the impact of health, education and social sector spending on vulnerable families
Provide input into predictive models based on strengths-based social investment approaches to complement the At-Risk model
Statistics NZ Objectives – this PPP
Support Statistics NZ to establish a formal programme of engagement with iwi/Māori for development of an appropriate data-driven infrastructure to meet the specific needs of iwi organisations

## Slide 3: Project Plan and Deliverables

## Slide 4: Access to area/mesh based data
Opportunity
Understand Iwi and Ethnic strength based indicators/measures against risk factors for place based services
Unrealised Opportunity
Difficult to view data due to:
confidentiality and access rules
in legislation and between SNZ and other government departments
by ethnicity, iwi, and to area or mesh block level
We also encountered the same issues for Education data by school
Problem solving approach to realise opportunity
Extracted data at an area level by iwi and ethnicity to identify where no result is returned in place of counts to understand impacts and options
Lifted location up to a higher level that needed, i.e. area not mesh block
Systemic changes required to fully realise opportunity
Standard design for access to data at area and mesh block level by ethnicity and iwi
Confidentiality and access protocols in place to protect individuals and enable iwi/NGO access for public good service delivery
Transparent and strategic prioritisation process to systematically increase access to connected data within protocols

## Slide 5: Ability to reconcile data to check reliability
Opportunity
To check confidence levels between government operational source data and IDI data results. Identify gaps and opportunities for improvement.
Unrealised Opportunity
Problems reconciling/checking data reliability and slow progress – need to have single source of truth, examples:
Data definitions did not match
Totals didn’t match for employed/unemployed when summarised by iwi/region /country
Difference of units and when used, e.g. region versus district
Difference of sources and matching, e.g. iwi classifications
Matching data totals between sources, years and across attributes, e.g. NCEA levels and UE qualifications at specific leaving ages
Problem solving approach to realise opportunity
Extracting and matching IDI and Government publically available to understand what could and couldn’t be matched and noting gaps
Systemic changes required to fully realise opportunity
To operationalise we will need:
Standard published data model
Full data dictionary
Defined processes for time bound data and attributes from extraction to end user
Access protocols to make data available to iwi/NGO’s based on need
Operational place based service delivery and strategic decision-making solutions
Data Model
Data Dictionary
Agreed Extract & Usage Standards

## Slide 6: Time taken to get access to data
Opportunity
Full scope coverage and testing findings with working and reference groups to test results, including mitigation plan to use the SIU Retail layer
Unrealised Opportunity
Problems encountered when trying to gain access to data:
Initial access approvals to IDI lab delayed work plan by 2 weeks
Output checking for basic census population data by area - estimated to take 2 weeks, took 2 months
Lab research access to view SIU Retail layer took 26 business days, confidentiality training still required.
Access delayed getting individual Department approvals
Problem solving approach to realise opportunity
Project SNZ analyst undertook to complete the output 1 check
Systemic changes required to fully realise opportunity
Streamline project access process
Broaden access process to include analytical and operational purposes as well as research and statistics
Streamline data release process
Consider authorising by organisation with the access and use of data agreed by contract and security protocols
This will be essential for iwi/NGO place based services.

## Slide 7: Other Systemic lessons to fully realise opportunity
Project planning and resource allocation
Appoint a SNZ project manager team during the proposal stage
Have an integrated and detailed plan with interdependent projects identified from the start
Provide the project manager with control over committed resources against estimates
Project team initiation and access to deliverables
Involve the whole delivery project team from the beginning so that requirements, expectations and commitments on both sides are understood and/or resolved before the project starts
The SNZ lead(s) must have pre-arranged authority and access to track all project deliverables
Relationship management and Governance
Continues a project lead and Senior Sponsor from the Maori Strategic Advisor team, who understands iwi partnership requirements
Formalise the governance structure and process to include projects and partners across all iwi/NGO partnership projects
Project and operational delivery skill sets need to be broadened
Address gaps and/or consider solution outside the SNZ IDI infrastructure, that removes access to data constraints within agreed parameters and protocols
Widen mix of skills to design and deliver an Operational decision-making solution rather than a Researcher based solution